UNCLASSIFIED // SYNTHETIC TEST DATA
Harbor Scribe Steering Group Minutes
Pilot readiness and rollout governance
Revision: Minutes v1.0 | Date: 27 May 2028

# 1. Meeting Overview

The Harbor Scribe steering group met to review pilot readiness, network dependencies, training design, and early performance metrics. Attendees included depot operations, cybersecurity, training leads, and supplier support representatives. The discussion intentionally balanced readiness concerns against visible process gains so the group would not reduce the decision to a single yes/no question.

At the time of the meeting, the pilot transition was still carried against 22 Jul 2028 even though multiple members expected movement. The meeting's purpose was to decide whether maintaining the old date preserved value or merely preserved appearances.

# 2. Decisions and Discussion

Cybersecurity reported that network segmentation review remained open. Operations acknowledged that pushing ahead without closure would create manual workarounds and undermine user confidence. Training leads reported that first-shift adoption was improving but second-shift confidence remained uneven. Depot leadership emphasized that an orderly launch after a short delay would be preferable to an on-time launch that required paper fallbacks in the highest-traffic areas.

Quality and performance slides showed encouraging throughput trends, with backlog age in digitized areas declining from about 18.2 days toward values near 11.6 days. The steering group agreed that these gains justified continued investment even though the pilot date needed reconsideration.

| Topic | Decision / Observation |
| --- | --- |
| Network segmentation | Remain as gate; do not waive |
| Training | Add refresher support, especially second shift |
| Pilot timing | Permit controlled move if readiness not complete |
| Performance trend | Backlog age improving in digitized flow |

# 3. Action Items

The steering group assigned actions to complete site survey validation, finalize revised training materials, and prepare an updated rollout baseline in the workbook. Lattice Harbor Software was asked to support dashboard refinement. Depot operations agreed to identify champions in each shop to reduce reversion to paper notes when scanners misread labels.

# 4. Interpretation

These minutes matter because they show that the later movement to 19 Aug 2028 was not driven only by cybersecurity. Training quality, user confidence, and readiness discipline were part of the decision. A RAG system focused solely on network terminology would miss that broader rationale.

# Appendix A. Dependencies and Interfaces

This document sits inside a broader execution thread for Harbor Scribe Depot Maintenance Digitization under contract SYN-DM-28-5602. Readers should expect related information to appear in planning notes, workbooks, meeting records, and other formal reports. The program office intentionally distributes truth across those artifacts: schedules tend to be most explicit in workbooks, supplier obligations are often clearest in statements of work or proposals, and causal explanations may appear first in draft notes before they are restated in a controlled format.

Key interfaces in this program include the prime organization Harbor Scribe Solutions, suppliers such as Lattice Harbor Software, Docklight Analytics, and execution sites including Redstone Depot and Paint Barn 2. Similar entity names also appear elsewhere in the corpus, so analysts should use program context rather than string similarity alone when joining evidence.

# Appendix B. Assumptions and Management Attention Items

Management assumptions embedded in this document include stable access to facilities, timely review cycles, and disciplined change control. If any of those assumptions erode, the resulting schedule or cost impact may appear first in the associated workbook rather than in a revised narrative. This is a normal feature of program execution and is deliberately represented here to create realistic retrieval conditions.

Leadership attention is focused on maintaining internal consistency across technical, schedule, supplier, and financial reporting. A document that looks authoritative but still carries superseded dates or draft estimates should be interpreted carefully. Users evaluating a RAG system should therefore expect some questions to require choosing the latest controlled source rather than the most verbose source.

# Appendix C. Referenced or Related Artifacts

Related artifacts include narrative notes, financial or schedule workbooks, and supplier-facing packages. Some questions can be answered from this file alone; others require cross-document synthesis, for example linking a milestone move to a supplier issue, or connecting a requirement threshold to a later test result. That cross-reference burden is intentional and is one of the main design goals of the corpus.