## Summary
UNCLASSIFIED // SYNTHETIC TEST DATA
Asterion ISR Payload Modernization
SYN-AV-28-1042
Current ETC ($M) | 49.58
Prior ETC ($M) | 47.8
Delta ($M)
CDR Current | 2028-09-26
EVT Current | 2028-12-09

## Budget
UNCLASSIFIED // SYNTHETIC TEST DATA
Asterion ISR Payload Modernization
SYN-AV-28-1042
WBS Element | Prior ETC ($M) | Current ETC ($M) | Delta ($M)
Systems Engineering | 6.42 | 6.93
Payload Structures | 8.15 | 8.94
Power and Thermal | 7.84 | 8.62
Supplier Tooling | 5.12 | 5.49
Integration and Test | 9.61 | 10.33
Program Management | 4.88 | 4.95
Quality and CM | 2.41 | 2.53
Management Reserve | 3.37 | 1.79
Total

## IMS
UNCLASSIFIED // SYNTHETIC TEST DATA
Asterion ISR Payload Modernization
SYN-AV-28-1042
Milestone | Baseline Date | Current Date | Variance (days) | Comment
CDR | 2028-08-14 | 2028-09-26 | 43 | Moved after ECP-04 approval
EVT Start | 2028-11-04 | 2028-12-09 | 35 | Delta qualification and rework
FA Lot 1 Integration Release | 2029-01-29 | 2029-02-18 | 20 | Supplier and design-change convergence

## Staffing
UNCLASSIFIED // SYNTHETIC TEST DATA
Asterion ISR Payload Modernization
SYN-AV-28-1042
Month | Systems Eng FTE | I&T FTE | Quality FTE | Total FTE
Jul-28 | 18 | 26 | 7
Aug-28 | 19 | 28 | 7
Sep-28 | 20 | 29 | 8
Oct-28 | 20 | 31 | 8
Nov-28 | 21 | 32 | 8
Dec-28 | 20 | 31 | 8
Jan-29 | 18 | 28 | 7

## Assumptions
UNCLASSIFIED // SYNTHETIC TEST DATA
Asterion ISR Payload Modernization
SYN-AV-28-1042
ID | Assumption
A1 | ECP-04 fully implemented before EVT entry
A2 | North Coast Systems LLC delivers first article rings by 15 Oct 2028
A3 | No further redesign beyond TI-88 / LAS-2B package
A4 | Management reserve partially consumed to cover approved change