## DeployPlan
UNCLASSIFIED // SYNTHETIC TEST DATA
Blue Mica Tactical Communications Refresh
SYN-CM-29-1188
Wave | Unit | Baseline Date | Current Date | Systems | Comment
Wave 1 | 1st Brigade | 2028-11-18 | 2028-11-18 | 164 | Completed pilot fielding
Wave 2 | 3rd Brigade | 2029-01-15 | 2029-02-06 | 188 | Moved due compliance and training prep
Wave 3 | Support Battalion | 2029-03-03 | 2029-03-10 | 96 | Dependent on lessons learned

## FieldingCosts
UNCLASSIFIED // SYNTHETIC TEST DATA
Blue Mica Tactical Communications Refresh
SYN-CM-29-1188
Category | Cost ($M)
Travel and site setup | 4.38
Field labor | 5.72
Packaging and kitting | 2.16
Comms / admin support | 2.36
Total

## Spares
UNCLASSIFIED // SYNTHETIC TEST DATA
Blue Mica Tactical Communications Refresh
SYN-CM-29-1188
Item | Description | Qty | Unit Cost | Extended ($M)
BAT-214 | Battery pack | 220 | 2400
ENC-21M | Crypto module spare | 12 | 28200
AMP-3 | Amplifier spare | 28 | 11600
Total

## Training
UNCLASSIFIED // SYNTHETIC TEST DATA
Blue Mica Tactical Communications Refresh
SYN-CM-29-1188
Element | Hours | Rate | Cost ($M)
Instructor prep | 280 | 120
Wave delivery | 420 | 135
Quick-reference package | 1 | 740000
Total

## KPI
UNCLASSIFIED // SYNTHETIC TEST DATA
Blue Mica Tactical Communications Refresh
SYN-CM-29-1188
Metric | Baseline | Current
First-pass issue completion (%) | 78 | 89
Serialized discrepancy rate (%) | 6.4 | 2.1
Average user support ticket closure (days) | 5.8 | 3.4