## Requirements
UNCLASSIFIED // SYNTHETIC TEST DATA
Ember Reach Radar Processing Module Procurement
SYN-RD-29-3324
Requirement | Threshold | Unit | Comment
Processing efficiency | 6.2 | GOPS/W | Minimum at first article
Shock survivability | 20 | g | Environmental threshold
Lead time | 22 | weeks | Maximum for Lot 1
Thermal margin | Pass/fail | qualitative | Validated in first article

## PriceComparison
UNCLASSIFIED // SYNTHETIC TEST DATA
Ember Reach Radar Processing Module Procurement
SYN-RD-29-3324
Supplier | Unit Price ($) | NRE ($M) | Lead Time (wks)
Summit Circuits | 118400 | 0.96 | 20
Helion Micro Devices | 111900 | 1.18 | 25
Halcyon Microdevices | 125600 | 0.74 | 18

## Scorecard
UNCLASSIFIED // SYNTHETIC TEST DATA
Ember Reach Radar Processing Module Procurement
SYN-RD-29-3324
Supplier | Technical | Schedule | Cost | Overall
Summit Circuits | 84 | 90 | 85 | 86.2
Helion Micro Devices | 91 | 72 | 84 | 83.4
Halcyon Microdevices | 78 | 82 | 77 | 79.1

## Schedule
UNCLASSIFIED // SYNTHETIC TEST DATA
Ember Reach Radar Processing Module Procurement
SYN-RD-29-3324
Milestone | Baseline | Current | Notes
Source Selection | 2028-12-12 | 2028-12-09 | Completed
First Article Test | 2029-02-14 | 2029-02-28 | Executed
ORR | 2029-04-11 | 2029-05-09 | Moved after corrective action

## Risks
UNCLASSIFIED // SYNTHETIC TEST DATA
Ember Reach Radar Processing Module Procurement
SYN-RD-29-3324
Risk ID | Description | Severity | Mitigation
E-04 | Thermal spreader HSK-12 may underperform | Medium | Adopt HSK-12B after FAT if required
E-07 | Packaging material long lead | Medium | Early procurement
E-11 | Overreliance on incumbent tribal knowledge | Low | Structured transfer board