## ResourcePlan
UNCLASSIFIED // SYNTHETIC TEST DATA
Harbor Scribe Depot Maintenance Digitization
SYN-DM-28-5602
Function | Headcount | Comment
Site readiness | 6 | Survey and network support
Trainers | 5 | Includes second shift
Scanning support | 4 | Device support and labels
Data / KPI | 3 | Dashboard and backlog metrics

## KPI
UNCLASSIFIED // SYNTHETIC TEST DATA
Harbor Scribe Depot Maintenance Digitization
SYN-DM-28-5602
Metric | Legacy Baseline | Current Pilot
Average backlog age (days) | 18.2 | 11.6
Digital capture rate (%) | 0 | 82
Duplicate traveler events / week | 14 | 4

## Rollout
UNCLASSIFIED // SYNTHETIC TEST DATA
Harbor Scribe Depot Maintenance Digitization
SYN-DM-28-5602
Site / Event | Baseline | Current | Reason
Redstone pilot go-live | 2028-07-22 | 2028-08-19 | Network segmentation and readiness
Paint Barn expansion | 2028-09-09 | 2028-09-30 | Label and scanner hardening
Second depot onboarding | 2028-10-14 | 2028-10-28 | Training cadence

## Training
UNCLASSIFIED // SYNTHETIC TEST DATA
Harbor Scribe Depot Maintenance Digitization
SYN-DM-28-5602
Training Block | Hours
Supervisor workshop | 36
Maintainer hands-on | 84
Second-shift refresher | 24
Train-the-trainer | 18
Total

## Issues
UNCLASSIFIED // SYNTHETIC TEST DATA
Harbor Scribe Depot Maintenance Digitization
SYN-DM-28-5602
Issue ID | Description | Severity | Owner
H-03 | Wireless dead zones in Paint Barn 2 | Moderate | Cyber / IT
H-07 | Barcode read reliability with overspray | Moderate | Ops
H-14 | Network segmentation review open | High | Cyber / IT