## IMS
UNCLASSIFIED // SYNTHETIC TEST DATA
Iron Vale Autonomous Ground Vehicle Integration
SYN-GV-28-2317
Milestone | Baseline | Current | Variance (days) | Driver
Subsystem fit check | 2028-11-01 | 2028-11-08 | 7 | Vehicle access and part availability
Endurance retest | 2029-01-08 | 2029-02-06 | 29 | Cooling retrofit integration
Limited User Test | 2029-02-12 | 2029-03-21 | 37 | Cooling retrofit plus suspension spares

## Risks
UNCLASSIFIED // SYNTHETIC TEST DATA
Iron Vale Autonomous Ground Vehicle Integration
SYN-GV-28-2317
Risk ID | Description | Probability | Impact | Mitigation Cost ($M) | Owner
R-09 | Dust ingestion in SHD-18 causing endurance failure | High | High | 0.68 | Engineering
R-12 | Front suspension CR-12 casting shortage | Medium | High | 0.2 | Supply Chain
R-15 | Retrofit install labor congestion in Bay 3 | Medium | Medium | 0 | Integration
Total Mitigation

## TestMatrix
UNCLASSIFIED // SYNTHETIC TEST DATA
Iron Vale Autonomous Ground Vehicle Integration
SYN-GV-28-2317
Metric | Requirement | Actual | Status
Endurance distance (km) | 120 | 94 | Fail
Mission completion (%) | 85 | 81 | Fail
Turning radius (m) | 5.8 | 5.5 | Pass

## CostOptions
UNCLASSIFIED // SYNTHETIC TEST DATA
Iron Vale Autonomous Ground Vehicle Integration
SYN-GV-28-2317
Option | NRE ($M) | Unit Price ($) | Qty | Extended ($M) | Notes
Aegis shroud retrofit | 0.42 | 18600 | 24 |  | 12-week lead time
Procedural cleaning only | 0.05 | 1200 | 24 |  | Does not meet endurance intent

## Staffing
UNCLASSIFIED // SYNTHETIC TEST DATA
Iron Vale Autonomous Ground Vehicle Integration
SYN-GV-28-2317
Month | Bay Techs | Test Crew | Software | Total
Oct-28 | 14 | 9 | 4
Nov-28 | 15 | 9 | 4
Dec-28 | 15 | 10 | 5
Jan-29 | 16 | 10 | 5
Feb-29 | 16 | 11 | 5
Mar-29 | 18 | 12 | 6